## Cover
An illustration of the application of Failure Modes and Effects Analysis (FMEA) techniques to the analysis of information security risks
Introduction and acknowledgement
The original version of this spreadsheet was kindly provided to the ISO27k Implementers' Forum by Bala Ramanan to demonstrate how the FMEA method can be used to analyze information security risks. Subsequently, Bala kindly agreed to donate it to the ISO27k Toolkit. Apart from minor updates and reformatting, it is essentially unchanged. We are very grateful for Bala's input.
Contents
The FMEA Sample tab has the actual illustration - an analysis of possible failure modes for a firewall.
The Guidelines provide additional notes on the FMEA method, including a step-by-step process outline.
The Severity, Probability and Detectability tabs have tables demonstrating scales commonly used to rank risks by these criteria.
Copyright
This work is copyright © 2008, ISO27k Forum, some rights reserved. It is licensed under the Creative Commons Attribution-Noncommercial-Share Alike 3.0 License. You are welcome to reproduce, circulate, use and create derivative works from this provided that (a) it is not sold or incorporated into a commercial product, (b) it is properly attributed to the ISO27k Implementers’ Forum at www.ISO27001security.com, and (c) derivative works are shared under the same terms as this.
Disclaimer
Risk analysis is more art than science. Don't be fooled by the numbers and formulae: the results are heavily influenced by the accuracy of the users' assessment of risk factors, by the definition of information assets and by the framing of risks being considered. For these reasons, the process is best conducted by a team of people with solid expertise and practical experience of (a) assessing and managing information security risks, and (b) the organization, its internal and external situation with respect to information security. Don't expect to get definitive answers from anyone. It is impossible to guarantee that all risks have been considered and analyzed correctly. Some very experienced practitioners in this field claim that all risk analysis is basically bunkum, and we have some sympathy with that viewpoint.
The results of the analysis should certainly be reviewed by management (ideally including IT auditors, Legal, HR, other support functions and/or information security consultants) and may be adjusted according to their experience, so long as the expert views are taken into consideration. Remember: just because the organization has little if any experience of a particular informaiton security risk does not necessarily mean that it can be discounted. Organizations with immature security management processes and systems may have significant ongoing security incidents that are not even recognized, due to inadequate incident detection and reporting processes.

## Guidelines
Guideline to Carry out a Risk Assessment Using FMEA
Important notes:
This method does not consider asset values. Rrisks are identified for each asset and prioritized without taking account of the asset values.
The Cumulative risk for the identified asset for each threat is ascertained by the Risk Priority Number (RPN)
Each asset can have more than one failure mode and for each failure mode there can be more than one vulnerability
How to carry out the Risk Assessment (RA) using FMEA:
1 | Identify the assets or the services rendered by the department under the scope of RA
5 | Now identify the failure modes for the identified asset/function. Please note that there could be more than one vulnerabilities for each asset
6 | Now identify the impact if the identified failure mode happens. That if the identified failure mode happens what will be the effect on the business or service.
7 | Now refer the impact chart and choose the number relevant to the effect of the failure mode
8 | Now identfiy the cause for the failure mode. Please note that each vulnerability can be linked with more than one threat.
9 | Now refer to the probability chart and choose the number that is more relevant to the frequency of the threat happening.
10 | Now list down the current controls. Kindly categorize the controls as preventive and detective controls. Write each control in separate rows.
11 | Now refer to the vulnerability chart and choose a number relevant to the size of vulnerability for each asset and the effectiveness of the controls that might have.
12 | Input all three in the corresponding fields. You can now see the Risk Priority Number calculated for a failure mode of the respective asset function.
13 | Now if the RPN is not under the acceptable value then the risk status shows "HIGH RISK", recommendation to mitigate each of these HIGH RISK has to be listed down. Kinldy list each control in separate rows.
Using prioritized risks
Management may decide to target, say, the top 5% of risks initially. This is an arbitrary value that can be reviewed/adjusted later.
Following the FMEA method, the risks are assessed, RPNs calculated and then risks are ranked by RPN.
5% of 1000 (the maximum RPN value) is 50. So any RPN above 50 requires review and (probably) control improvements.
All risks with RPNs above 50 are identified as "HIGH RISK". This criterion is of course based on the arbitrary 5% value noted above.
If the organization is well controlled with relatively few HIGH RISK items, the 5% value may be extended to, say 15% to address lower risks.
Alternatively, if there are simply too many HIGH RISK items to tackle at once, they may be addressed in top-down sequence according to the RPNs.
The prioritized list of risks provides management with a rational basis for determining how much resource to apply to risk reduction: the cutoff point should go further down the list if more resources are allocated, and vice versa.

## FMEA Sample
A/A | Asset Name | Function | Potential Vulnerability | Potential Threat | Potential Business Consequence (Impact) | Impact | Likelihood | Current Controls |  | Vulnerability | RPN
[8 empty] | Preventive Controls | Detective Controls
1 | Domain Controller / File Server | 1)Verifies users on computer network. 2)Stores industry data (high value non personal data) | Rules not appropriately configured | Excessive Privilege Abuse | Inability to verify users on the network. Inability to access data | 10 | 8 | Strict and grant database access base on the user roles requirements |  | 5 | 400
2 | Industry Employee Data | Employees information | Database not encrypted | Insider Employee gets employee personal data | Disclosure or modification of personal information | 8 | 6 | Internal Employee Rules and Procedures available | Log Monitoring | 7 | 336
3 | Edge-Router | packet filtering , routing packages | incomplete package sender authentication | access to the network of unauthorized user | non authorised users send or receive confidential data | 8 | 4 | 1)Mandatory Access Control 2)Use of firewall 3)Frequent firmware updates 4)Frequent password change 5)Block of dangerous websites | Log Monitoring | 4 | 128
4 | Industry Customer Data | Customers' Information | Database not encrypted | Access to customer information | Disclosure or modification of customers' personal information | 9 | 6 | Database encryption |  | 7 | 378
5 | Create New Customer | Procedure to create a new customer | Insufficient check of input data | Incorrect input of data | Inability to correctly create a new customer | 5 | 7 | Verification of input data |  | 3 | 105
6 | Create New Order (Local) | Procedure to create a new order locally | Insufficient check of input data | Incorrect input of data | Inability to correctly create new local orders | 6 | 7 | Verification of input data |  | 3 | 126
7 | Create New Order (Remotely) | Procedure to create a new order remotely | Insufficient check of input data | Incorrect input of data | Inability to correctly create new remote orders | 6 | 7 | Verification of input data |  | 3 | 126
8 | Customer Support | Procedure to communicate with customers | Weak server | DDoS Attack | Inability to address and help customers' problems and requests | 4 | 2 | Block an IP after its sent packets exceed a certain limit |  | 4 | 32
9 | Windows 10 Pro | Operating System used by workstations | Not frequent Updates | Malware Attack | Infected OS | 7 | 6 | Frequent Updates |  | 7 | 294
10 | Windows 7 | Operating System used by workstations | Not frequent Updates | Malware Attack | Infected OS | 7 | 6 | Upgrade to a more recent OS |  | 8 | 336
11 | LAPTOP1 | Director's workstation | Weak password | Interception of director's data | Disclosure of director's business information | 7 | 6 | 1)Use of strong passwords 2)Frequent Updates 3)Use of strong antivirus 4)Frequent web browser updates | Intrusion Detection System | 9 | 378
12 | PC5 | Workstation in the Sales&IT Department | Not frequent Updates | Interception of sales' data | Illegal leak of sales' data | 5 | 6 | 1)Use of strong passwords 2)Use of 2FA 3)Frequent Updates 4)Use of strong antivirus 5)Frequent web browser updates | Intrusion Detection System | 7 | 210
13 | CRM SERVER | Manages and automates industry to customer interaction and sales | Non-functional air condition | Inappropriate operating conditions | Server goes offline/malfunctions and the interaction between industry to customer is lost | 8 | 8 |  | 1)Use of thermometer to monitor the room's temperature and warn when it goes off limits 2)Log Monitoring | 4 | 256
14 | RADIUS/SNMP SERVER | 1)Provides authentication, authorization, accounting 2)Manages the network and its devices | Default configuration usage | Unauthorized access to company's network | Anyone can access and control the company's network | 9 | 7 | 1)Use of appropriate configuration to strengthen the security of the database 2)Mandatory Access Control 3)Use of unique password | Log Monitoring | 8 | 504
15 | ROUTER2 | Connects Sales&IT and Accounting&HR Departments to the backbone of the network | 1) Old firmware usage 2) Not frequent Updates | 1)Unauthorized access 2)Routing protocol attack 3)Interception of incoming and outgoing data 4)Masquerade attack 5)DHCP spoofing | Router malfunctions and the connection between the routers is disrupted | 8 | 3 | 1)Use of firewall 2)Frequent firmware updates 3)Frequent password change 4)Block of dangerous websites |  | 7 | 168
16 | VOIP-PHONE1 | Used in the Sales&IT Department | Unprotected cables | Wear of exposed cables | Phone cannot be used or there is corruption of signal | 4 | 2 | Proper cable management to avoid exposure | Monthly checks on the cables | 2 | 16
17 | ROUTER3 | Connects Director's Office to the backbone of the network | 1) Old firmware usage 2) Not frequent Updates | 1)Unauthorized access 2)Routing protocol attack 3)Interception of incoming and outgoing data 4)Masquerade attack 5)DHCP spoofing | Router malfunctions and the connection between the routers is disrupted | 8 | 3 | 1)Use of firewall 2)Frequent firmware updates 3)Frequent password change 4)Block of dangerous websites |  | 7 | 168
18 | WIRELESS-LAN-CONTROLLER1 | Controls the Access Point in Director's Office | Incorrect configuration | Man in the middle attack | Sniff of director's traffic | 7 | 7 | Use of appropriate configuration |  | 5 | 245
19 | TABLET-PC1 | Director's Personal Tablet | Weak password | Interception of director's data | Disclosure of director's personal information | 6 | 7 | 1)Use of strong passwords 2)Use of strong antivirus | Intrusion Detection System | 9 | 378
20 | EMAIL SERVER | Allows the exchange of emails with any internet user | Weak spam filter | Malicious email | Server is infected with malware | 9 | 8 | Use of strong spam filter | Log Monitoring | 8 | 576
21 | PC4 | Workstation in the Sales&IT Department | Deprecated Operating System | Interception of sales' data | Illegal leak of sales' data | 5 | 7 | 1)Use of strong passwords 2)Use of 2FA 3)Upgrade to a more recent OS 4)Use of strong antivirus 5)Frequent web browser updates | Intrusion Detection System | 9 | 315
22 | PC6 | Workstation in the Sales&IT Department | Deprecated Operating System | Interception of sales' data | Illegal leak of sales' data | 5 | 7 | 1)Use of strong passwords 2)Use of 2FA 3)Upgrade to a more recent OS 4)Use of strong antivirus 5)Frequent web browser updates | Intrusion Detection System | 9 | 315
23 | PRINTER1 | Used in the Account&HR Department | 1)Unrestricted remote access 2)Unencrypted data transmission | 1)Excessive use by the employees for personal gain 2)Interception of data to be printed | Lost resources and disclosure of printed documents | 6 | 3 | Encrypted data transmission |  | 3 | 54
24 | DNS/DHCP SERVER | 1)Names the computer netowrks 2)Allocates network addresses | Uncontrolled data input in cache | Cache poisoning/phishing attack | Redirects traffic to untrusted sites | 9 | 7 | 1)Use of the most current version 2)Run only the required services allowed to do so | Log Monitoring | 7 | 441
25 | HRM SERVER | Monitors employees' progress | Default configuration usage | Modification of metrics/data | Interferes with the proper monitoring of employee progress | 8 | 5 | 1)Use of appropriate configuration 2)Mandatory Access Control 3)Use of uniqe password | Log Monitoring | 5 | 200
26 | SW-FLOOR4.1 | Connects RADIUS, CRM and Application servers to Router4 | 1)Unlimited MAC addresses per port 2)Reception of ARP in untrusted ports | 1)MAC flooding 2)STP attack 3)ARP attack 4)VLAN hopping attack | 1)Sniff of passing traffic 2)Attacker becomes a man in the middle 3)Can access other VLANs | 9 | 7 | 1)Use of certain limit of MAC Address per port 2)Receive ARP packets only in trusted ports |  | 7 | 441
27 | ROUTER1 | Connects the Firewall to the backbone of the network | 1) Old firmware usage 2) Not frequent Updates | 1)Unauthorized access 2)Routing protocol attack 3)Interception of incoming and outgoing data 4)Masquerade attack 5)DHCP spoofing | Router malfunctions and the connection between the routers is disrupted | 8 | 3 | 1)Use of firewall 2)Frequent firmware updates 3)Frequent password change 4)Block of dangerous websites |  | 7 | 168
28 | SW-FLOOR4.2 | Connects Email, Domain Controller, DNS and HRM servers to SW-FlOOR4.1 | 1)Unlimited MAC addresses per port 2)Reception of ARP in untrusted ports | 1)MAC flooding 2)STP attack 3)ARP attack 4)VLAN hopping attack | 1)Sniff of passing traffic 2)Attacker becomes a man in the middle 3)Can access other VLANs | 9 | 7 | 1)Use of certain limit of MAC Address per port 2)Receive ARP packets only in trusted ports |  | 7 | 441
29 | ROUTER4 | Connects SW-FLOOR4.1 to the backbone of the network | 1) Old firmware usage 2) Not frequent Updates | 1)Unauthorized access 2)Routing protocol attack 3)Interception of incoming and outgoing data 4)Masquerade attack 5)DHCP spoofing | Router malfunctions and the connection between the routers is disrupted | 9 | 3 | 1)Use of firewall 2)Frequent firmware updates 3)Frequent password change 4)Block of dangerous websites |  | 7 | 189
30 | APPLICATION SERVER | 1)Manages the interaction between the industry and its customers 2)Handles HTTP requests and interacts with the CRM server | Default configuration usage | DDoS Attack | Denies service of the server for the time period the attack is happening | 10 | 8 | 1)Use of appropriate configuration 2)Block an IP after its sent packets exceed a certain limit | Log Monitoring | 5 | 400
31 | PC3 | Workstation in the Sales&IT Department | Not frequent Updates | Interception of sales' data | Illegal leak of sales' data | 5 | 6 | 1)Use of strong passwords 2)Use of 2FA 3)Frequent Updates 4)Use of strong antivirus 5)Frequent web browser updates | Intrusion Detection System | 7 | 210
32 | PC1 | Workstation in the Accounting&HR Department | Deprecated Operating System | 1)Interception of logistical data 2)Interception of employee data | Disclosure of logistical documents and of employees' personal information | 7 | 7 | 1)Use of strong passwords 2)Use of 2FA 3)Upgrade to a more recent OS 4)Use of strong antivirus 5)Frequent web browser updates | Intrusion Detection System | 9 | 441
33 | PC2 | Workstation in the Accounting&HR Department | Deprecated Operating System | 1)Interception of logistical data 2)Interception of employee data | Disclosure of logistical documents and of employees' personal information | 7 | 7 | 1)Use of strong passwords 2)Use of 2FA 3)Upgrade to a more recent OS 4)Use of strong antivirus 5)Frequent web browser updates | Intrusion Detection System | 9 | 441
34 | SW-FLOOR2 | Connects PC3, PC4, PC5, PC6 and VOIP-Phone to Router2 | 1)Unlimited MAC addresses per port 2)Reception of ARP in untrusted ports | 1)MAC flooding 2)STP attack 3)ARP attack 4)VLAN hopping attack | 1)Sniff of passing traffic 2)Attacker becomes a man in the middle 3)Can access other VLANs | 8 | 6 | 1)Use of certain limit of MAC Address per port 2)Receive ARP packets only in trusted ports |  | 7 | 336
35 | ACCESS POINT | Grants internet access to LAPTOP1 and TABLET-PC1 | Doesn't use VPN | Evil twin attack by an employee | Insider employee sniffs director's data | 7 | 7 | Use VPN |  | 7 | 343
36 | SW-FLOOR1 | Connects PC1, PC2 and Printer1 to Router2 | 1)Unlimited MAC addresses per port 2)Reception of ARP in untrusted ports | 1)MAC flooding 2)STP attack 3)ARP attack 4)VLAN hopping attack | 1)Sniff of passing traffic 2)Attacker becomes a man in the middle 3)Can access other VLANs | 8 | 6 | 1)Use of certain limit of MAC Address per port 2)Receive ARP packets only in trusted ports |  | 7 | 336
37 | SW-FLOOR3 | Connects the Wireless Controller and the Access Point to Router3 | 1)Unlimited MAC addresses per port 2)Reception of ARP in untrusted ports | 1)MAC flooding 2)STP attack 3)ARP attack 4)VLAN hopping attack | 1)Sniff of passing traffic 2)Attacker becomes a man in the middle 3)Can access other VLANs | 8 | 6 | 1)Use of certain limit of MAC Address per port 2)Receive ARP packets only in trusted ports |  | 7 | 336
39
40
Note on C1: List down the fucntion or purpose of the asset. If more than one purpose is identified for the identified service list them down separately
Note on D1: In what all ways the service running on this asset can fail? ie the vulnerabilities List down each failure mode separately
Note on E1: if the vulnerability happens, then what could be the effect of the failure? If there is more than one failure list them seperately
Note on G1: Refer Severity Table
Note on H1: Refer Probabilty Table
Note on I1: Identify the current controls vis a vis preventive and detective controls. If there are more than one, then list them separately
Note on K1: Refer Detection table

## Impact
Effect | Impact of Threat realisation | Ranking
Catastrophic | Resource not available / Problem unknown | 10
Extreme | Resource not available / Problem known and cannot be controlled | 9
Very High | Resource not available / Problem known and can be controlled | 8
High | Resource Available / Major violation of policies | 7
Moderate | Resource Available / Major violations of process | 6
Low | Resource Available / Major violations of procedures | 5
Very Low | Resource Available / Minor violations of policies | 4
Minor | Resource Available / Minor violations of process | 3
Very Minor | Resource Available / Minor violations of procedures | 2
None | No effect | 1

## Likelihood
PROBABILITY of Failure | Failure Prob | Ranking
Very High: Threat is almost inevitable | >1 in 2 | 10
| 1 in 3 | 9
High: Repeated Threat occurences | 1 in 8 | 8
| 1 in 20 | 7
Moderate: Occasional Threat occurences | 1 in 80 | 6
| 1 in 400 | 5
| 1 in 2,000 | 4
Low: Relatively few Threat occurences | 1 in 15,000 | 3
| 1 in 150,000 | 2
Remote: Threat occurence is unlikely | <1 in 1,500,000 | 1

## Vulnerability
Vulnerability | Ranking
The vulnerability is very exposed and directly, remotely exploitable, and its exploitation could result in severe impacts. Relevant security control or other remediation is not implemented and not planned; or no security measure can be identified to remediate the vulnerability. | 10
The vulnerability is exposed and exploitable, and its exploitation could result in severe impacts. Relevant security control or other remediation is not implemented and not planned; or no security measure can be identified to remediate the vulnerability. | 9
The vulnerability is of very high concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is planned but not implemented | 8
The vulnerability is of high concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is planned but not implemented | 7
The vulnerability is of moderate concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is partially implemented and somewhat effective. | 6
The vulnerability is of moderate concern, based on the exposure of the vulnerability and ease of exploitation and/or on the severity of impacts that could result from its exploitation. Relevant security control or other remediation is implemented and effective. | 5
The vulnerability is of minor concern, but effectiveness of remediation could be improved. Relevant security control or other remediation is fully implemented and somewhat effective | 4
The vulnerability is of minor concern, but effectiveness of remediation could be improved. Relevant security control or other remediation is fully implemented and effective | 3
The vulnerability is not of concern. Relevant security control or other remediation is fully implemented, assessed, and effective | 2
There is no vulenrability | 1